## Project Plan
Completed Tasks
Current Pending Tasks
Late Completed Tasks
Future Tasks
Week 1 - 06/20 to 06/24 | Task | Description | Start Date | Estimated Completion Date | Actual Completion Date | Remarks | Priority
| Work on the Timer | The game will run until the number of seconds configured in the configuration file is matched | 2016-06-20 | 2016-06-23 | 2016-06-21 | Created disco_config.properties file and added timer configuration related parameters. Completed the timer functionality for the game. Please verify | Low
| Start on the Scoring Criteria / Target Inspection | Refer the design document and bridge the gap betweem what needs to be done and what is already done | 2016-06-23 | 2016-06-24 | 2016-06-26 | Status as on 06/25 - Completed Target Inspection and Scoring Criteria ( without Tracking Points Calculation). Score configuration stored in disco_config properties file | High
| Creating scenarios with multiple targets to test Scoring | Testing a unique scenario with multiple targets with each target associated to an image. The target properties are stored in disco_config.properties file. Modifying the scenario xml file to add extra targets and changing the target attributes | 2016-06-23 | 2016-06-23 | 2016-06-23 | Additional Target Attributes added to the xml file : imagePath, priorityType and status. All Target Images will be placed inside images folder with a resolution of less than 50 X 50. Added priorityLevels="HIGH,MEDIUM,LOW" for setting different values as true identites for targets | Low
| Appearance and Disappearance of Units | Incorporating the concept of Active and In-Active units in the scenario xml file. Button click event based appearance and disappearance of units | 2016-06-26 | 2016-06-26 | 2016-06-26 |  | High
Week 2 - 06/27 to 07/01 | Structuring of Scenario xml template | Modify the design of exisiting senario xml file so that It looks structured enough to make changes to the xml file | 2016-06-27 | 2016-06-30 | 2016-06-29 | Took one day off on Tuesday (06/28). The Scenario xml has been formatted and structured in a user friendly editable format | High
| Control the Speed of the Objects | We need to reduce the speed of the objects by a factor of 10. Modify/Change the existing algorithm to reduce the current speed of the objects | 2016-07-01 | By the weekend | 2016-07-06 | Able to control the speed of the targets and units movement. Can still improve on reducing the choppiness | High
Week 3 - 07/05 to 07/06 | Organize the Movement of units while we modify the positioning of the units | When the units are directed to move from one place to another, the movement is random with an exception to one unit. We need to control the algorithm to organize the random movement of units | 2016-07-05 | 2016-07-07 | 2016-07-15 |  | High
| Control the flickering of the targets | When the target comes inside the range of the units, the target flickers itself to be visible. Modify the algorithm to control the movement of the target so that it is continous | 2016-07-08 | By the weekend | Same task posted to Week 6 |  | High
Week 4 - 07/11 to 07/15 | Briefing button functionality | The briefing functionality needs to updated with the current task that needs to be performed for the game and it will be scenario specific. The details should be fetched from config file and it should be dynamic | 2016-07-13 | 2016-07-13 | 2016-07-13 | Completed laying out the basic structure of the briefing window. Added one more Status tab to view basic information about objects | Low
| Functioning of Overlay viewing button | Work on functioning of the toggable overlay button which enables the user to view the search area boundaries | 2016-07-14 | By the weekend | Same task posted to Week 6 |  | High
Week 5 - 07/18 to 07/22 | Work on the Factors Sorrounding Unit ReLocation and Unit Launch | The positioning of the units for creating a testing environment Blue Units and Red Untis ReLocation Works good independently After a Unit Launch, Check the Relocation After a Unit Transfer, Check the Relocation Check the Relocation movement for more number of units --> overlapping of units | 2016-07-18 | 2016-07-20 | 2016-07-26 | Status as on 07/19 - Randomness in the unit relocation movement has been effectively reduced and unit relocation movement shows some good improvement for both red and blue units. Launch and relocate works fine independently but not parallely. Also relocate while launch needs a lot of improvisation. Status as on 07/20 - Stuck with the Parallel Unit Launch Blue and Red Units. Status as on 07/24 - Completed Parallel Unit Launch ( Red and Blue Units ) Status as on 07/26 - Completed all types of unit movements ( unit launch and unit transfer) | High
Week 6 - 07/25 to 07/29 | Control the flickering of the targets | When the target comes inside the range of the units, the target flickers itself to be visible. Modify the algorithm to control the movement of the target so that it is continous | 2016-07-27 | 2016-07-28 | 2016-07-28 |  | High
| Functioning of Overlay viewing button | Work on functioning of the toggable overlay button which enables the user to view the search area boundaries | 2016-07-29 | By the weekend | 2016-07-29 |  | High
| Providing alpha numeric values as identities for targets and units | Modifying the id values for units and targets to accept alpha-numeric values as well. | 2016-07-29 | 2016-07-29 | 2016-07-29 |  | Medium
Week 7 - 08/01 to 08/05 | Activity Feed Updation | Remove all existing fillers with which the current activity feed has been implemented. Update the Activity Feed with Live moments from the game. Ability to activate and deactivate all or some of the messages | 2016-08-01 | 2016-08-02 | 2016-08-04 | Configurable Activity Feed Information is updated in the XML file for the User to turn on/off all or specific fields. It gives live updates of every user action and also it gives an update every 10 seconds about the current status of the game | High
| Resource pool for purchasing sensors | A value which is set at the beginning of the game and controls how many units can be launched (each unit has a cost and launching it deducts from the pool) Add unit property of 'cost' to xml | 2016-08-02 | 2016-08-04 | 2016-08-05 | The Total Available Credit Limit and Indivudual Unit Price is configured in the XML file. The User will be able to launch unit only if the unit price falls below the avaiilable credit limit. | High
Week 8 - 08/08 to 08/12 | Data Collection format | Updating the Data Collection format to add some information about all the objects and other stuffs as discussed | 2016-08-08 | 2016-08-09 | 2016-08-10 | Completed adding all possible user interactions and generated a comprehensive csv file separated by buffer columns | High
| Configurable User Controls | All User Controls should be configured in the XML file and we shall be able to enable / disable all types of User Controls ( Especially Hiding Unit Proximity, Unit Launching ... etc) | 2016-08-10 | 2016-08-11 | 2016-08-11 | All Possible Controls are Configured in the XML file. The Admin can now disable or enable any control to change its visibility criteria | Medium
| No dependency on the config file | Copy all the properties that are configured in the config file and add it to the xml file. All the properties shall be configured only in the xml file | 1 | Migrated all the properties from Config file. I haven't deleted the Config file yet, so that we can refer to certain descriptions assigned to each property. However, the code will still work without config file. |  |  | High
| Data Collection format | Nathan to provide the format for Data Collection. | Data Collection Format Recieved
| Change Cohesion to Search Area | Change the Label 'Cohesion' to 'Search Area' | 0 | Changed the label from "Cohesion" to "Search Area" |  |  | Low
| Configurable User Controls | All User Controls should be configured in the XML file and we shall be able to enable / disable all types of User Controls ( Especially Hiding Unit Proximity, Unit Launching ... etc) | 2 | All Possible Controls are Configured in the XML file. The Admin can now disable or enable any control to change its visibility criteria |  |  | Medium
| Appearance of Units (Advanced) | Launching different units with diverse profiles | Same is updated in Week 5 |  |  |  | High
| Activity Feed Updation | The Activity feeds needs to updated as and when there is a new update or when the user makes any progress in the game. Activity feed needs to be an option in the XML file for turning off and on features. | Same is updated in Week 7 |  |  |  | Low
Karishma
Week 1 oct 11
| briefing button | Make the pane of equal size of the game window(or desktop) with the image covering 3/4 part and text on the right | 2016-10-11 | 2016-10-17 | 2016-10-20 | Briefing window made of size of the game window. With image and text area distribution changed to look similar to the game map and buttons panel. | Medium
| Relocation detect radius | set the detection radius for all units to certain measure, so as to redus their deetction capacity. It should be unit specific | 2016-10-20 | 2016-10-25 | 2016-10-27 | Relocation detect radius can be set difefrent for difefrent units from the xml file. tested for one case, keepig target at constant location and relocating unit to that location. | high
week 3 oct 27
| Background graphic | Allow the user to select an image for changing the backgroud of the map region | 2016-10-27 | 2016-11-04 | 2016-11-03 | Image for map can be set through the xml file. 2 colors can be used for shading, these names are also given in the xml file with the image path. | medium
week 4 nov 3
| different relocation speed | All the user to set the relocation speed | 2016-11-03 | 2016-11-10
week 5- nov 7
| Gui visibility Bugs | proximity and search scale and labels still visible when made deactive | 2016-11-08 | 2016-11-10 | 2016-11-08 | search area and proximity labels and drop down boxes made to disappear when Proximity and Cohesion Slider pro[erties from xml file are set to" N"
| overlay Button | error when the overlay button is pressed | 2016-11-08 | 2016-11-10
| unit launch button | label and the drop down are visible even when the launching is deactivated | 2016-11-08 | 2016-11-11 | 2016-11-08 | Launch unit label and drop down made invisible when the functionality is set to "N" in demo file
| freezing of the game | when relocation is set to the same seeking range, game freezes | 2016-11-08 | 2016-11-22
| relocation pattern | relocation movement should be symmetric | 2016-11-08 | 2016-11-22
| Unit seek button | clicking on the seek button makes all the targets visible | 2016-11-08 | 2016-11-10 | 2016-11-08 | Seek button is removed. Sea.java file has comented code incase the button has to be back
| credit limit visibility | Make the credit limit easily invisible | 2016-11-08 | 2016-11-08 | 2016-11-08 | xml file has a field of credit limit under user controls to make it possible to enable or dsble the viewing
week5 nov 10
| Downwards counting counter | downward counting of timer in seconds and minutes | 2016-11-10 | 2016-11-10 | 2016-11-10 | DOWNWARDS counting of the counter can be set by changing the xml field
| Abbility to change image of view target dialog box | image in the view target dialog box should be chageable and can be different than the target image | 2016-11-10 | 2016-11-10 | 2016-11-10 | xml field added with an inspectionImage field to hold teh path of image added to the vie target dialog box
week6 nov 11 | feedback from the first trial
| targets being visvisle when group button are clicked | when the group buttons are clicked all the targets are being visible | 2016-11-10 | 2016-11-25 | 2016-12-06 | Changed show for view target in target. When Group button is clicked, targets will not be visible
| group switching | group switching is ineffective when one unit of a new group is added | 2016-11-10 | 2016-11-25
| unit launch movement speed | very slow speed from launching area to the search area | 2016-11-10 | 2016-11-27
| unit launching for a new group | when new group is launching a unit.the units are not seeking. Make them active | 2016-11-10 | 2016-12-06
| errors when map image named incorrectly in the xml file | keep background color when map image name in xml file is incorrect | 2016-11-10 | 2016-11-22 | 2016-11-17 | code modified to set the map image only with the backgroud color when image path is wrong, so that program wont crash
Important
| targets move to bottom left when alowwed for movement | include an arraylist for destination locations and then make the targets move to those points | 2016-11-10
| seek behaviour | Make the see behaviour more uniform to avoid locking of the unit | 2016-11-10
| button ability to chnage the seeking style | can be linear, arc etc | 2016-11-10
| relocation uniformity | make the relocation uniform to avoid the overlappping (birds movements) | 2016-11-10
| freezing of game | freezing of game when the units are relocated in the same search area | 2016-11-10
Pending Tasks to be Planned |  |  | estimated number of days | remark
| Intersection of Blue and Red Units | Collision of Blue and Red Units while they relocate creates lot of problems. Making sure that there are no collisions while both the units are relocating | 2 |  |  |  | High
| Target WayPoint Movement | Change the type of target movement from Random to customized type of movement. The Admin should be able to provide various co-ordinates (waypoints) and make the target to move across the configured set of waypoints | 5 |  |  |  | Medium
| Background Graphic | Ability to sub in and out a background image instead of the current blank map | ? | Current graphic setup is not structured in a way to allow easy manipulation of stationary graphical items on screen. |  |  | Low
Future Tasks | Providing distinct set of priority levels | At present, the priority levels are set as HIGH and LOW. In future, there may be a requirement to change the priority levels. Config file and minor code changes needs to be implemented for this change |  |  |  |  | Low

## Updated Sheet
Completed
Currently working on
Unable to move ahead
needs attention
PENDING TASKS By 02/01/2017
| TASK | DESCRIPTION | PRIORITY | EXP COMPLETION BY | REMARKS/SUGESSTIONS
| Different Relocation speed | relocation speeds should be different for different units and users should be able to set the same | 1A
| Overlay error | overlay button function gives error
| freezing of game | when relocation is set to the same seeking range, game freezes | 2
| reloctaion pattern | Relocation pattern should be symmetric and not random, to avoid overlapping
| group switching | Group switching is ineffective when a new group unit is launched
| New group unit Launching | Launching an unit of a new group gives errors and units are not active
| Unit launching speed | When unit of same griup is lauched it moves to the search area, relatively slower than the seeking speed of teh present units | 1B |  | speed changed for relocation and launchin but blue unit launching is not working correctly
| Target accumulation at bottom left | when tragets are allowed for movement, all move to the bottom left area of the screen
| Seek Behaviour | Seek pattern should be more uniform to avoid locking of units
| Button ability to change the seek pattern | Button to the UI, that will enalble user to select if the seeking should be linear, arc etc
| Finding the movement pattern | Find anything that controls the unit movement and make sure that it is the same across the unit launching, relocation, how do they behave | 1
| instructions for updating the workspace | share it on drive with nathan , karen. |  | 2017-02-01 | Find the file titled "How to update Disco" in the shared "Disco" folder in google drive
| insrtrutions for not overwritting the files | share it on drive with nathan , karen. |  | 2017-02-01 | Find the file titled "How to update Disco" in the shared "Disco" folder in google drive
| Complete Demo file | Find the Demo file that has all the features and uplod it to the drive making a making a note of it |  | 2017-02-02 | Demo 3 is the file with all the properties required.Aslo a word document of all properties required in a demo file is added to the drive
| Fix target inspection window and capabilities | When you find a target and click view target, the target inspection window is very small and will now allow you to actually identify the target
| Temporarily allow me Karen to see where the target ships are | In order to create scenarios I need to be able to see where the target ships are during the game instead of just guessing. Can you allow this? I know it has been a possibility in the past | *** Needs to be priority |  | find the scenario file"forTesting" and refer "Changed File list" | Added an xml propertty "testing". Y: makes all the targets visible, N hides all the targets as before
| Increased effect of proximity | Currently the units are still fairly close together when you increase the proximity to 100
| Relocation movement is jerky | When the units are moving from one place to another the movement is still very jerky
| Allow visibility of overlawy when you choose to move the units | When you click to move the units you should be able to see a quick image of where the search area is
create a jar file and upload the new version of the file on drive by tonight

## Bug Tests
Bug Status | Bug/problem | Desired behavior | Found by | Resolved By | Notes | Date Resolved
Resolved | Exiting pop up windows with the X in upper right closes the entire game | X should behave like the close button. | NH | PS | Issue has been resolved. X button will not shut down the main program. | 2016-08-10
Unresolved | Right Clicking on units while search area and proximity are on highest for both red and blue, with three blue units out freezes the game | Right Clicking should allow movement of units | CK
Unresolved | After hitting play, an immediate right click on the blue units without changing any other setting freezes the game | Right Clicking should allow movement of units | CK
unresolved
unresolved | Speed when units are moving to a search area does not speed up | manipulating speed in the code should manipulate the speed while in transit | KG
unresolved | Can repeatedly click view target and get extra points, should only be able to do once | make it so it is only allowed once | KG
unresolved | search area will randomly move to match other color group | area is only participant designated | KG
unresolved | target will get stuck in the corner | target should continue moving once tracked in search area | KG